## Slide 1
LOCKHEED MARTIN · CISS PROGRAM
Internship Delivery Approach
Masdar City afternoons · common foundation · capstone-driven depth
A 36-week teaching model for CISS interns. Experts travel from the Software Development Center at Al Dhafra AFB to the Lockheed Martin office in Masdar City. Curriculum is not rewritten until this approach is agreed.
SEPTEMBER 2026
UNCLASSIFIED | FOR OFFICIAL USE

## Slide 2
PURPOSE
Agree the delivery model before rewriting training material
Ask: How do Lockheed Martin experts at Al Dhafra teach a 36-week internship that lives at Masdar City — without turning every afternoon into a commute problem, and without teaching defense services?
01
Define the operating picture
Who travels, where teaching happens, and how a five-day afternoon cadence maps to four disciplines.
02
Lock the 36-week phasing
Common foundation, capstone kickoff, weekly work loop, military insertion, and a possible SDC phase.
03
Name the first-four-week topics
General, useful literacy per discipline — before any track dives into its craft.
CISS INTERNSHIP | DELIVERY APPROACH
Purpose
02

## Slide 3
OPERATING PICTURE
Experts stay at the SDC. Teaching happens at Masdar.
SOFTWARE DEVELOPMENT CENTER
Al Dhafra AFB
Home station for the Lockheed Martin technical team. Systems Engineering, Networking, System Administration, and Software experts work here. Interns are not based here for the first 24 weeks.
One SME travels each afternoon · Mon–Fri
CISS PROJECT OFFICE
Masdar City
Lockheed Martin office where the CISS internship and capstone live. Interns stay here. Morning is intern work time. Afternoon is instruction by the visiting SME.
All lectures and capstone work for weeks 1–24
~30 MINUTES
drive between sites
The intern cohort does not commute to the air base for class. One expert from one discipline goes to Masdar each afternoon. After week 24, selected students may come to the SDC — if approvals are in place. They are not in place today.
CISS INTERNSHIP | DELIVERY APPROACH
Operating picture
03

## Slide 4
PROGRAM AT A GLANCE
Four Lockheed Martin disciplines. SE is the spine.
36
Week internship
4
LM teaching disciplines
5
Afternoons at Masdar
24
Weeks before any SDC option
SE
Systems Engineering
Mandatory entire 36 weeks. Coordinates the capstone.
NET
Networking
Elective after week 4. Path, policy, and protection.
ADMIN
System Administration
Elective after week 4. Hosts, identity, and runtime.
SW
Software Development
Elective after week 4. Build, integrate, and ship.
MILITARY LECTURES are not a fifth daily commute. They are inserted as needed — and only after review against the Technical Assistance Agreement so they are not treated as defense services.
CISS INTERNSHIP | DELIVERY APPROACH
Program at a glance
04

## Slide 5
GUIDING PRINCIPLES
Six rules that keep the model simple
1
Take the expert to the intern
Masdar is the classroom. SDC is home station. We do not move the cohort to the air base for daily class.
2
Common first, specialty later
Weeks 1–4 are general and useful for every intern. Depth waits until people have a shared vocabulary.
3
SE never becomes optional
After week 4, interns choose which other disciplines to keep attending. Everyone stays in Systems Engineering.
4
The capstone organizes the work
Week 5 opens the project. From week 6, each afternoon reviews last week’s work, teaches, exercises, and assigns next week’s capstone tasks.
5
Military is inserted, not assumed
Ops lectures are scheduled when they help — and only if TAA review says they are not defense services.
6
SDC access is a maybe
After week 24, a student in a given discipline may train at the SDC. Approvals are not in place. The plan of record stays Masdar.
CISS INTERNSHIP | DELIVERY APPROACH
Principles
05

## Slide 6
36-WEEK PHASING
Four phases. One classroom. Depth after a shared base.
01
WEEKS 1–4
Common foundation
All interns attend every lecture. Each discipline teaches general, useful material. No specialty dive. No capstone tickets yet.
02
WEEK 5
Capstone kickoff
SE presents the project overview. Each discipline presents what its part must accomplish. Interns see the whole problem before they specialize.
03
WEEKS 6–24
Depth + weekly work
Electives open. SE remains mandatory. Each afternoon: review last week, teach, exercise, assign next week’s capstone work. Military inserted as needed.
04
WEEKS 25–36
Finish at Masdar; SDC optional
Same Masdar cadence continues. Students in a discipline may start SDC training only if approvals land. Do not plan as if they will.
CISS INTERNSHIP | DELIVERY APPROACH
Phasing
06

## Slide 7
ATTENDANCE MODEL
Everyone together for four weeks. Then SE plus choice.
WEEKS 1–4 · ALL LECTURES
Every intern attends Systems Engineering, Networking, System Administration, and Software.
Purpose is a shared language: how a packet moves, how a host is run, how code is changed, how a requirement is written.
No one is “already a network intern” in week 2. Specialization is a later decision, not a first-day label.
Friday remains available for workshops or a TAA-cleared military lecture.
WEEK 5 ONWARD · SE + ELECTIVES
All students continue Systems Engineering for the rest of the program. That is not negotiable.
Interns then decide which of Networking, Admin, and Software they will keep attending.
An intern may keep more than one elective if the weekday cadence allows. They may also drop one later.
Week 5 is still all-hands: every intern hears the capstone overview and every discipline’s work statement.
CISS INTERNSHIP | DELIVERY APPROACH
Attendance
07

## Slide 8
WEEKLY RHYTHM · PROPOSED
One SME, one afternoon, one discipline — Monday through Friday
Morning at Masdar is intern work time on last week’s assignment. Afternoon is instruction. Friday is the flex day so military lectures can be worked in without stealing a technical afternoon.
MON
Systems Engineering
ALL 36 WEEKS
Spine of the week. Artifacts, reviews, and capstone integration.
TUE
Networking
ALL → THEN ELECTIVE
Path, addressing, policy, and later the three-site fabric.
WED
Software
ALL → THEN ELECTIVE
Git and craft first; then the simulator, daemon, and client.
THU
System Admin
ALL → THEN ELECTIVE
Hosts and identity first; then provision, certs, and harden.
FRI
Flex
AS NEEDED
SE workshop, integration, or a TAA-cleared military lecture.
CISS INTERNSHIP | DELIVERY APPROACH
Weekly rhythm
08

## Slide 9
WEEKS 1–4
General and useful — not a four-week specialty school
Each discipline gets four afternoons with the whole cohort. Teach what every intern will still need on week 30, whether they stay in that room or not. Hold the deep craft until electives open.
DO TEACH
Vocabulary the other tracks will use (requirement, VLAN, certificate, merge request).
How to think: evidence, owners, versions, and “what would we test?”
Safe habits: unclassified work, no secrets in Git, change control, least privilege.
Enough practice that a Thursday assignment is possible without a lab that only specialists can finish.
DO NOT TEACH YET
Juniper commit models, OSPF/BGP/MPLS, or IPsec design.
FreeIPA, vSAN, Ansible, or host-hardening playbooks.
JDBC pools, ActiveMQ resource adapters, JavaFX, or Jenkins pipelines.
The PRSAS architecture, ICDs, or role tickets — that is week 5.
CISS INTERNSHIP | DELIVERY APPROACH
Weeks 1–4 intent
09

## Slide 10
FOUNDATION TOPICS · SYSTEMS ENGINEERING
Four afternoons: the chain before the design
WEEK 1
What SE is
Why programs fail when people jump to design
Vision as a shared picture
Stakeholders and needs grammar
Artifacts have owners and versions
WEEK 2
Needs → use cases
Who benefits, and so that what
Actors and the main success scenario
Extensions and rejected use cases
Trace: need traces_to use case
WEEK 3
Requirements
Shall language and EARS patterns
Acceptance criteria that prove the shall
IDs, NFRs, and testability
Do not hide design inside a requirement
WEEK 4
Reading the system
Context, structure, and deployment views
A simple sequence and a simple state
Verify vs validate in plain language
How SE will coordinate the other three
CISS INTERNSHIP | DELIVERY APPROACH
SE foundation
10

## Slide 11
FOUNDATION TOPICS · NETWORKING
Four afternoons: packets, paths, and how to prove them
WEEK 1
How a network is built
LAN vs WAN and device roles
Switch, router, firewall — who does what
OSI / TCP-IP enough to debug a conversation
Why software is useless if the packet never arrives
WEEK 2
Addressing
IPv4, mask, and default gateway
DHCP and DNS in operational terms
What a subnet is for
Write an address plan a peer can read
WEEK 3
Conversations on the wire
TCP vs UDP and when each is used
Common ports (SSH, HTTPS, DNS, AMQP)
VLAN and NAT as ideas, not configs
The allowed-path mindset
WEEK 4
Test before you guess
Ping, traceroute, and layered evidence
What “it doesn’t work” is not allowed to mean
Change control at intern level
Hold Junos, OSPF, BGP, MPLS, IPsec
CISS INTERNSHIP | DELIVERY APPROACH
NET foundation
11

## Slide 12
FOUNDATION TOPICS · SYSTEM ADMINISTRATION
Four afternoons: the host is the system’s runtime
WEEK 1
Linux on a VM
RHEL-class guests, not Docker-first
Filesystem, users, processes
systemctl and what a service is
Least privilege as a habit
WEEK 2
See what the machine is doing
Logs, journalctl, and reading without drowning
Symptom → hypothesis → test
Tickets: incident vs change vs request
Evidence packs a peer can reuse
WEEK 3
Software on the host
Packages: what gets installed, and from where
Why “works on my laptop” is not a deployment
Secrets never live in Git or a screenshot
Backup and snapshot as ideas
WEEK 4
Trust and identity
What a certificate is, in one page
Why every box should not have its own password file
How admin work shows up in SE V&V
Hold FreeIPA, vSAN, Ansible, NFS Kerberos
CISS INTERNSHIP | DELIVERY APPROACH
Admin foundation
12

## Slide 13
FOUNDATION TOPICS · SOFTWARE DEVELOPMENT
Four afternoons: change control, then how software talks
WEEK 1
Git as daily craft
Clone, branch, commit, push
History you would not be ashamed of
Recovery without destroying the repo
Branch names tied to a ticket
WEEK 2
How a team ships a change
Ticket → branch → review → merge
What a good review comment looks like
Program tools vs lab tools (same habits)
You do not merge your own unchecked work
WEEK 3
Reading and writing code
Python may be how you think; Java is the contract language
Read someone else’s function before writing yours
Secrets, credentials, and integrity
Code implements a requirement — it does not invent one
WEEK 4
Services, not scripts
A process that talks to a database
A process that publishes/consumes a message
Why an ICD exists before a parser
Hold JDBC pools, JavaFX, Jenkins, ActiveMQ RA
CISS INTERNSHIP | DELIVERY APPROACH
Software foundation
13

## Slide 14
WEEK 5 · CAPSTONE KICKOFF
SE shows the whole problem. Each discipline shows its work.
SYSTEMS ENGINEERING — PROJECT OVERVIEW
Prototype Radar Situational Awareness System (PRSAS): two simulated radars, a secure path to a central site, a track processor, a database, and an authenticated air-picture client. Unclassified lab only. Not a live C2 system.
SE must accomplish
CONOPS, MBSE artifacts, track schema, V&V, virtualization study, lessons-learned. Owns the shared contracts the others build against.
Networking must accomplish
Three-site topology, least-privilege firewalls, site-to-site encryption, path validation, and a replayable configuration guide.
Admin must accomplish
VM provisioning, identity, lab certificates, host hardening, and enough automation that the stack can be rebuilt.
Software must accomplish
Radar-message simulators, track-processing daemon, situational-awareness client, and end-to-end integration with the other tracks.
CISS INTERNSHIP | DELIVERY APPROACH
Week 5
14

## Slide 15
WEEKS 6 AND BEYOND
Every afternoon is the same four-part loop
01
Review
Look at last week’s assigned capstone work. What is done, what is wrong, what is blocked. This is not a status meeting that skips the artifacts.
02
Teach
New material for the discipline — now at depth. Junos, identity, Java services, architecture, and so on, always in service of the project.
03
Exercise
Do something in the room. A config, a diagram, a failing test, a log pack. Interns leave with muscle memory, not only notes.
04
Assign
Work to be accomplished during the following week on the capstone. Due when that discipline meets again. SE assignments continue for everyone.
WHAT “DEPTH” MEANS HERE
Networking goes into Junos, zones, routing, and tunnels. Admin goes into identity, certificates, virtualization, and hardening. Software goes into Java, PostgreSQL, messaging, daemons, and the client. SE goes into CONOPS, behavior, ICDs, and V&V — with the whole class still in the room.
CISS INTERNSHIP | DELIVERY APPROACH
Weeks 6+
15

## Slide 16
MILITARY LECTURES
Worked in as needed — after TAA review, not before
Military content is useful so interns can talk to operators without pretending to be them. It is also the fastest way to step on the Technical Assistance Agreement. No lecture is scheduled until export/TAA review says it is not a defense service.
LIKELY SAFE TO REVIEW
Open-source UAE military structure, ranks, and public platforms
Unclassified CONOPS / AOC vocabulary as literacy, not instruction in how to fight
How an operator reads a picture — using the classroom SA system, not a fielded C2
Public planning terms (ATO as a document type) without planning a real mission
DO NOT TEACH UNTIL TAA SAYS YES
Tactics, techniques, procedures, or employment of weapons
Real basing, order of battle, ROE, or classified interfaces
How to plan or execute an actual air tasking cycle
Anything that would be “teaching them to operate a defense article”
CISS INTERNSHIP | DELIVERY APPROACH
Military / TAA
16

## Slide 17
WEEKS 25–36
Masdar remains the plan. SDC is a gated option.
What “may” means
Not in the plan of record
The 36-week Masdar afternoon cadence is what we staff and schedule. SDC on-site is an add-on.
By discipline, not as a cohort move
A student working a specific discipline may go to the SDC for training. This is not “the class relocates in week 25.”
Approvals are not in place
Base access, export, and host-nation/program permissions are still open. Do not brief interns that they will be at Al Dhafra.
If approvals land
Use SDC time for gear, labs, and work that cannot be done at Masdar. Keep SE and capstone integration on the Masdar rhythm unless that also gets approved.
BRIEFING LINE
After 24 weeks, selected students may train at the SDC if approvals are granted. Until then, all instruction is at Masdar City.
Do not write SDC weeks into the published intern calendar as a promise.
CISS INTERNSHIP | DELIVERY APPROACH
SDC option
17

## Slide 18
DECISIONS AND NEXT STEPS
Agree these items, then rewrite the material
1
Weekday map
Confirm Mon SE / Tue NET / Wed SW / Thu Admin / Fri flex — or name the swap.
2
Elective rule
Must an intern keep at least one specialty, or may they sit SE-only after week 4?
3
TAA owner
Who reviews each military lecture against the TAA before it is put on the calendar?
4
SDC chase
Who owns the approval path, and what is the earliest honest date we might hear?
AFTER AGREEMENT
1. Split each track into Foundation (W1–4), Kickoff (W5), and Depth (W6+).
2. Write the four Week-5 “what we must accomplish” briefs.
3. Build the weekly assign/review packets against the capstone, not against a generic syllabus.
4. Park military modules until TAA review returns a yes or a rewrite.
5. Leave SDC weeks off the intern-facing calendar until approvals exist.
CISS INTERNSHIP | DELIVERY APPROACH
Decisions
18